## Sheet1
TO DO | Instances |  |  | Assigned Member | Expected Date
Enemy Movement |  |  |  | John Krueger | 2019-03-26
Collisions |  |  |  | John Krueger | 2019-03-26
Game Over Screen |  |  |  | Jamie | 2019-04-02
Start Screen |  |  |  | Jamie | 2019-04-02
Sound Design | Shooting | Explosion | Music | Oliver | 2019-04-02
Difficulty Ramp |  |  |  | Noah | 2019-04-06
Enemy Ship Diversity |  |  |  | Noah | 2019-04-06
Powerups | Second Laser | Faster Movement | V A P O R W A V E | Noah | 2019-04-06
Pause Screen |  |  |  | Jamie | 2019-04-09
Particle Effects |  |  |  | John Krueger | 2019-04-12
Presentation Rough Draft |  |  |  | Oliver | 2019-04-16
Presentation Practice Run |  |  |  | Oliver | 2019-04-18
High Scores |  |  |  | Jamie | 2019-04-20
Settings Screen |  |  |  | Jamie | 2019-04-20
Working Game Prototype |  |  |  | John Krueger | 2019-04-20
Game Demo | Works on other computers |  |  | John Krueger | 2019-04-25
Debugging |  |  |  | John Krueger | 2019-04-27
Polish |  |  |  | Noah | 2019-04-27
Legend |  | Personal Goals
Core Gameplay loop |  | Game Completed | April 27th
Visual/audio components |  | Presentation Finished | April 30th
Logistics