## Sheet1
TO DO | Description | Instances |  |  |  | Assigned Member | Expected Date
Enemy Movement | Enemy movement and progressive movement speed | Speed Variablility | Zig Zag | Back and Forth | Homing on Player | John Krueger | 2019-03-26
Collisions | Creating enemy and bullet colllisions in game |  |  |  |  | John Krueger | 2019-03-26
Game Over Screen | Once the player is destroyed, a game over screen will be displayed |  |  |  |  | Jamie | 2019-04-04
Start Screen | To start the game, a Start Screen will be displayed and press the space bar to start the game |  |  |  |  | Jamie | 2019-04-04
Sound Design | In game sound for shooting, explosions and music | Shooting | Explosion | Music |  | Oliver | 2019-04-02
Difficulty Ramp | Increase in enemies spawned |  |  |  |  | Noah | 2019-04-06
Enemy Ship Diversity | As the game progresses, new and different ships spawn |  |  |  |  | Noah | 2019-04-06
Powerups | As the game progresses, powerups will spawn | Second Laser | Faster Movement | V A P O R W A V E |  | Noah | 2019-04-06
Pause Screen | The game can be paused and resumed |  |  |  |  | Jamie | 2019-04-09
Particle Effects | Effects are produced on collision, explosion, etc. | PRetty Sparkels |  |  |  | John Krueger | 2019-04-12
Presentation Rough Draft | A rough draft for class presentation |  |  |  |  | Oliver | 2019-04-16
Presentation Practice Run | In class game run |  |  |  |  | Oliver | 2019-04-18
High Scores | Implementation of high score saving and sorting |  |  |  |  | Jamie | 2019-04-20
Settings Screen | A setting screen with the ablity to adjust sound volume and controls |  |  |  |  | Jamie | 2019-04-20
Working Game Prototype | A working game prototype |  |  |  |  | John Krueger | 2019-04-20
Game Demo | Game demo that can work on other computers | Works on other computers |  |  |  | John Krueger | 2019-04-25
Debugging | Debugging the game |  |  |  |  | John Krueger | 2019-04-27
Polish | Cleaning the game, making it run smoother and look cleaner |  |  |  |  | Noah | 2019-04-27
Unit tests for one component | Testing for one component | [5 empty] | 2019-04-16
Progress report (Milestone 7) | [6 empty] | 2019-04-16
Legend |  |  | Personal Goals
Core Gameplay loop |  |  | Milestone 6 | April 2nd
Visual/audio components |  |  | Milestone 7 | April 16th
Logistics |  |  | Game Completed | April 27th
|  |  | Presentation Finished | April 30th
|  |  | Milestone 8 | May 1st